## Device Selector View
Task | Status | Comments | Winegard Comments
Add UUID filter for Winegard devices only | Completed | Currently not enabled for testing
Add connection status UI to inform user of connection status | Completed | Testing
Add tab bar for toggling between device manager and widgets |  | Tab bar added with custom icon images
add "My Devices" section
add "Add New Device" functionality

## Widget View
Task | Status | Comments | Winegard Comments
Create and add icon for log files view | Complete
Add tab bar for toggling between device manager and widgets |  | Tab bar added with custom icon images
Add app logic to enable access to widgets that don’t require connectivity to winegard device

## Channel Summary View
Task | Status | Comments | Winegard Comments
Add infographic for signal strength with color |  | Do we still want to add this given the current amount of information in the cell
Add method to go to individual channel view for selected channel cell | Started | Added info button to go to individual channel, still need to finish application logic to show correct channel when switching and select tab correctly
Add virtual channel to cell data and put physical channel in parentheses | complete
Fix bug causing collectionview to be removed from cell when cell is scrolled off screen | complete
Fix bug causing incorrect collectionview positioning when selecting certain cell index positions | Complete
Update channel summary asynchronously | Pending | Summary updating when no cells are selected

## Individual Channel View
Task | Status | Comments | Winegard Comments
Fit channel selection scroll view to fill screen | Complete
Add channel meta data to display: call sign, virtual and physical chanel, network logo, shows? |  | Sizing for the current screen will need to be revised for this to work on all screen sizes

## Spectrum Analyzer View
Task | Status | Comments | Winegard Comments
Add 4 additional labels to x-axis | Complete
Add additional labels to y-axis | Pending | Added mid range label. How many total?
Make 2 MHz the default resolution | Complete
Change scans per frequency to averaging and set default to none | Started
Add quick settings | Complete
Add data logging feature
Add vertical axis lines to graph | Complete
Add reset button to config menu

## Firmware Upgrade View
Task | Status | Comments | Winegard Comments
Write bootloader state machine | Complete
Design user interface | Pending | Need to get feedback from Winegard on current design
Create logging schema for software update process | Started | Determining which information should be included in log

## Map View
Task | Status | Joe Comments | Winegard Comments
Create custom Pin for towers on map | Pending | Added custom pin, need to get feedback from Winegard
Add popup to show same information provided for channel summary view | Started | Added rest data integration
Add ability for customer to enter location information manually or let the app find their location | Started

## Settings View
Task | Status | Comments | Winegard Comments

## Information View
Task | Status | Comments | Winegard Comments | Task | Status | Comments | Winegard Comments
Add ability to change BT name | Started
Add layout to display Bootloader version, App version, cypress part number, flash size, silicon rev, board revision | Started

## Log Files View
Task | Status | Comments | Winegard Comments
Define list of log file types |  | Need to know all of the types of logs we will be creating and providing accessibility to
Design user interface |  | Maybe tab view if there are only a few different types of log files
Code view controller

## Winegard RestAPI
Task | Status | Comments | Winegard Comments

## Data Logging
Task | Status | Comments | Winegard Comments
Create log data manager class to handle rayzar log data | Complete
impliment logData characteristic communication | Complete
create thread management for receiving both logData and antenna data at the same time | Complete
Investigate UI implications of managing logData from rayzar |  | This may add delays to UI based data such as the Sprectum analyzer view. Other views not as intensive so may not affect. Maybe no logging for spectrum analyzer view